{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Marketing Plan Data","List Data"],"not_rendered":{"defined_names":13},"read":"whole","date_system":"1900"}

{"sheet":"Marketing Plan Data","index":0,"n_rows":24,"n_cols":11,"rows_kept":24}
[]
[null,"Marketing Plan Data"]
[{"$nulls":3},"STATUS COLOR LEGEND & TOGGLE"]
[]
[]
[{"$nulls":3},"Not Started","In Progress","Delayed","Complete","Custom 1","Custom 2","Custom 3","Custom 4"]
[{"$nulls":3},"ON","ON","OFF","ON","OFF","OFF","OFF","OFF"]
[]
[{"$nulls":5},"ANTICIPATED",null,"ACTUAL",null,"COST"]
[]
[]
[null,"TASK","STATUS","OWNER","ASSIGNED TO","START DATE","END DATE","START DATE ","END DATE ","ESTIMATED","ACTUAL"]
[null,"Product Analysis","In Progress","John C.","John C.","2012-07-01","2012-08-01","2012-06-28",null,{"v":1500,"d":"$1,500"},{"v":1250,"d":"$1,250"}]
[null,"Design Storyboards","In Progress","Mark M.","John C.","2012-07-15","2012-08-15","2012-07-13",null,{"v":2000,"d":"$2,000"},{"v":1840,"d":"$1,840"}]
[null,"Review Storyboard Design","Complete","Mark M.","John C.","2012-08-01","2012-08-20",null,null,{"v":1450,"d":"$1,450"}]
[null,"Research Analysis Phase I","Delayed","Kamil A.","Andrew L.","2012-06-01","2012-07-01","2012-06-01","2012-06-28",{"v":3000,"d":"$3,000"},{"v":3200,"d":"$3,200"}]
[null,"Advertising Content Creation Phase I","Delayed","Kamil A.","Timothy S.","2012-09-01","2012-09-15",null,null,{"v":500,"d":"$500"}]
[null,"Product Requirement Definitions","Delayed","Kamil A.","Vivian A.",{"$nulls":4},{"v":575,"d":"$575"},{"v":125,"d":"$125"}]
[null,"Prototype Development Specifications","In Progress","Kamil A.","Gabe F.","2012-09-12","2012-09-25",null,null,{"v":1750,"d":"$1,750"}]
[null,"Quality Control, Progress Reports","In Progress","Mark M.","Kamil A.","2012-07-01","2012-10-01","2012-07-01",null,{"v":925,"d":"$925"},{"v":250,"d":"$250"}]
[null,"Create Storyboards","Not Started","Mark M.","John C.","2012-07-15","2012-08-15","2012-07-13",null,{"v":2000,"d":"$2,000"},{"v":1840,"d":"$1,840"}]
[null,"Review Storyboards with Graphic Artists","Delayed","Mark M.","John C.","2012-08-01","2012-08-20",null,null,{"v":1450,"d":"$1,450"}]
[null,"Research Analysis Phase II","Complete","Kamil A.","Andrew L.","2012-06-01","2012-07-01","2012-06-01","2012-06-28",{"v":3000,"d":"$3,000"},{"v":3200,"d":"$3,200"}]
[null,"Advertising Content Creation Phase II","Not Started","Kamil A.","Timothy S.","2012-09-01","2012-09-15",null,null,{"v":500,"d":"$500"}]

{"sheet":"List Data","index":1,"n_rows":14,"n_cols":3,"rows_kept":14}
[]
[null,"Marketing Plan Lists"]
[]
[]
[]
[null,"NAME","TITLE"]
[null,"John C.","Marketing Specialist"]
[null,"Mark M.","Marketing Manager"]
[null,"Kamil A.","Project Manager"]
[null,"Phil G.","Marketing Analyst"]
[null,"Andrew L.","Research Coordinator"]
[null,"Timothy S.","Marketing Specialist"]
[null,"Vivian A.","Marketing Analyst"]
[null,"Gabe F.","Associate Marketing Manager"]