{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Source Data","Days by Project","Hours by Project"],"not_rendered":{"charts":2,"images":1,"external_links":1},"unopened":[{"sheet":"Days by Project","index":1,"reason":"not_a_worksheet"},{"sheet":"Hours by Project","index":2,"reason":"not_a_worksheet"}],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Source Data","index":0,"n_rows":16,"n_cols":12,"rows_kept":16,"merged":[[0,0,0,1],[1,0,1,1]],"flags":["formulas_cached_only"]}
["<Company Name>  "]
["Project Time Performance Tracking"]
[]
[]
["Project Name","Project Type","Estimated Start","Estimated Finish","Estimated Days","Actual    Start","Actual Finish","Actual Days","Variance (in Days)","Estimated Hours","Actual Hours","Variance (in Hours)"]
["A. Datum Corporation","Business Continuity Planning","2004-01-04","2004-03-04",60,"2004-01-04","2004-03-09",65,5,200,220,20]
["Alpine Ski House","Cost Reduction","2004-01-20","2004-02-21",31,"2004-01-25","2004-02-20",25,{"v":-6,"d":"(6)"},400,390,{"v":-10,"d":"(10)"}]
["Baldwin Museum of Science","Process Improvement","2004-02-06","2004-04-16",70,"2004-02-10","2004-04-23",73,3,500,500,0]
["Blue Yonder Airlines","Cost Reduction","2004-02-24","2004-04-25",61,"2004-02-22","2004-04-29",67,6,150,145,{"v":-5,"d":"(5)"}]
["City Power & Light","Sarbanes-Oxley","2004-03-08","2004-03-18",10,"2004-03-09","2004-03-28",19,9,250,255,5]
["Coho Vineyard","Strategic Planning","2004-03-19","2004-04-29",40,"2004-03-19","2004-05-05",46,6,300,310,10]
["Coho Winery","Cost Reduction","2004-04-10","2004-04-20",10,"2004-04-12","2004-04-17",5,{"v":-5,"d":"(5)"},500,510,10]
["Coho Vineyard & Winery","Sarbanes-Oxley","2004-04-18","2004-05-12",24,"2004-04-17","2004-05-16",29,5,750,790,40]
["Contoso, Ltd.","Cost Reduction","2004-05-12","2004-06-22",40,"2004-05-15","2004-06-24",39,{"v":-1,"d":"(1)"},450,430,{"v":-20,"d":"(20)"}]
["Contoso Pharmaceuticals","Process Reengineering","2004-06-14","2004-08-12",58,"2004-06-16","2004-08-16",60,2,230,235,5]
["TOTAL",{"$nulls":3},404,null,null,428,24,{"v":3730,"d":"3,730"},{"v":3785,"d":"3,785"},55]