## Sheet1
PROJECT WORKSHEET
[Project Name]
[Company Name]
TASKS | START DATE | END DATE | DURATION
RESEARCH | 2017-09-22 | 2017-10-30 | 48
Vendor Acquisition, Customer base Probability Plan | 2017-10-22 | 2017-11-15 | 40
Exterior and Interior Design Plan, Site Proposal Plan | 2018-05-15 | 2018-05-30 | 16
PROCUREMENT | 2018-05-30 | 2018-06-25 | 27
Location Acquisition, Menu Development | 2018-08-21 | 2018-08-31 | 28
Permits and Business Registry | 2018-09-01 | 2018-09-03 | 29
Kitchen Equipment | 2018-09-04 | 2018-11-02 | 62
Renovation Materials | 2018-11-03 | 2018-11-28 | 27
RENOVATIONS | 2018-11-09 | 2018-12-15 | 40
Demolition, Construction and Repair | 2019-05-15 | 2019-05-30 | 15
Equipment Installations, Onsite Freezer | 2019-05-30 | 2019-06-25 | 30
ADVERTISING | 2019-08-21 | 2019-08-31 | 12
Newspapers / Phone Books | 2019-08-31 | 2019-09-10 | 18
Posters and Flyers | 2019-12-12 | 2020-01-04 | 6
Website | 2020-01-06 | 2020-01-18 | 13
Staff Help Wanted | 2020-01-10 | 2020-01-15 | 6