## Sheet1
Contract Payment Schedule
Contractor: |  | Owner:
[ABC Construction Company] |  | [John]
[806 Smith Avenue Duarte, CA 91010] |  | [10 High Point Dr. Ames, IA 50010]
[2025550114] |  | [2025550180]
Task | Estimated Duration (Days) |  | Status
Structural Modifications | 20 |  | In Progress
Resurfacing of Parking Slot | 10 |  | Completed
Purchase of Computers and Installations | 25 |  | Not Started
Electrical Modifications | 5 |  | Not Started
Plumbing Modifications | 13 |  | Completed
Interior and Exterior Painting | 3 |  | In Progress
Sheetrocking of Walls and Ceilings | 2 |  | Completed
Installation of Fixtures | 5 |  | Not Started
Landscaping | 10 |  | Not Completed on Time
Fire System for Drywall | 30
Alarm/Security Wiring | 19
Replacing Tiles | 6 |  | In Progress
Set Toilets, Sinks, etc. | 8 |  | Not Completed on Time
Total Payment Amount | 150000
Payment Approved | 142500
Note: If the task is not completed on time or defects found in it then payment will be processed after deducting 1%-5% of the claim amount.